## Risk Register
Risk ID | Category | Description | Probability | Impact | Risk Score | Risk Level | Mitigation Strategy | Owner | Status | Date Identified | Target Close Date
R-001 | Procurement | Steel procurement delay due to global supply chain disruptions impacting structural steel delivery | 4-High | 5-Critical |  |  | Pre-order critical steel items early; identify alternative suppliers in Mexico and Canada | Sarah Chen | Open | 2025-08-13 | 2025-12-16
R-002 | Weather | Unusually heavy rainfall delaying foundation excavation and concrete pour schedule | 3-Medium | 4-Major |  |  | Install temporary shelter structures; monitor 14-day forecast; add schedule buffer for Q2 | Mike Torres | Open | 2025-09-06 | 2025-10-19
R-003 | Labor | Labor shortage of skilled ironworkers during peak erection phase | 4-High | 4-Major |  |  | Partner with local trade unions; offer per-diem incentives; recruit from adjacent states | James Wilson | Open | 2025-07-31 | 2025-12-17
R-004 | Design | Design change request from owner for expanded concourse width after slab pour | 3-Medium | 3-Moderate |  |  | Establish formal change order process; require owner sign-off before rework; track impact | Rachel Kim | Open | 2025-08-09 | 2025-10-06
R-005 | Procurement | Fabrication error in custom steel trusses for roof spanning main arena | 2-Low | 5-Critical |  |  | Mandate third-party shop drawing review; require mill certification for all steel | Sarah Chen | Open | 2025-09-30 | 2026-03-07
R-006 | Safety | OSHA fine exposure from fall protection violations on upper deck steel | 2-Low | 4-Major |  |  | Daily safety briefings; dedicated safety monitor per zone; full-body harness inspection | David Park | Open | 2025-12-01 | 2026-04-09
R-007 | Labor | Concrete batch plant strike delaying all ready-mix deliveries for 3 weeks | 2-Low | 4-Major |  |  | Pre-qualify backup batch plant 50 km radius; stockpile 500 CY of aggregate on site | James Wilson | Open | 2025-09-26 | 2026-01-02
R-008 | Budget | Budget overrun on site utilities relocation — water main and high-voltage lines | 3-Medium | 4-Major |  |  | Re-estimate utility relocation with civil engineer; request contingency release | Lisa Patel | Open | 2025-09-05 | 2025-10-20
R-009 | Schedule | Permit delay from city planning department for structural occupancy certificate | 3-Medium | 3-Moderate |  |  | Hire expediter; submit 2 weeks ahead of schedule; maintain daily follow-up with city | Maria Gonzalez | Open | 2025-10-26 | 2026-03-28
R-010 | Procurement | Supply chain hold on HVAC rooftop units due to copper coil shortage | 3-Medium | 3-Moderate |  |  | Order units 8 weeks ahead of need; accept partial shipment with temporary units | Sarah Chen | Open | 2025-07-18 | 2025-08-29
R-011 | Design | Settlement risk in soil below main column footings discovered during excavation | 2-Low | 5-Critical |  |  | Complete geotechnical boring analysis before footing design; engineer-reviewed fill spec | Rachel Kim | Mitigated | 2025-09-21 | 2025-12-21
R-012 | Logistics | Crane mobilization delay due to road weight restrictions on access route | 3-Medium | 3-Moderate |  |  | Secure oversize load permits 30 days in advance; scout secondary route | Mike Torres | Open | 2025-09-11 | 2026-02-21
R-013 | Procurement | Electrical subcontractor default mid-project — bonding and insurance validation missed | 2-Low | 4-Major |  |  | Pre-qualify all subcontractors; maintain list of 3 backup trades per discipline | Sarah Chen | Open | 2026-02-04 | 2026-07-05
R-014 | Budget | Inflation-driven material cost increase exceeding 15% of budgeted line items | 4-High | 4-Major |  |  | Include escalation clause in all contracts; lock pricing with 90-day material commitments | Lisa Patel | Watch | 2025-12-23 | 2026-05-05
R-015 | Logistics | Sports field turf installation delayed by port congestion on imported artificial turf rolls | 3-Medium | 4-Major |  |  | Order turf early; use domestic alternative supplier; re-sequence turf to later float | Mike Torres | Open | 2025-07-26 | 2025-10-03
R-016 | Safety | Coordinated scaffolding collapse endangering workers on east elevation | 1-Very Low | 5-Critical |  |  | Daily scaffold tag inspection; licensed erector required for all assembly above 20 ft | David Park | Closed | 2026-01-15 | 2026-05-28
R-017 | Procurement | Scoreboard/video board custom LED panels have 12-week lead time beyond schedule | 4-High | 3-Moderate |  |  | Place order at NTP; expedite shipping via air freight for last 10% of panels | Sarah Chen | Open | 2025-06-13 | 2025-08-27
R-018 | Labor | Lack of qualified welders to meet ASME code on pipe welding for mechanical systems | 3-Medium | 3-Moderate |  |  | Recruit from pipeline project winding down; provide AWS certification bonus | James Wilson | Open | 2025-11-05 | 2026-02-11
R-019 | Design | Foundation waterproofing membrane failure at underground parking level | 2-Low | 4-Major |  |  | Specify premium membrane system; require installer certification; add drain board layer | Rachel Kim | Open | 2025-10-14 | 2026-03-17
R-020 | Schedule | City council rezoning vote threatens stadium parking lot expansion footprint | 2-Low | 4-Major |  |  | Engage lobbyist; present traffic study early; have alternate stacked parking design ready | Maria Gonzalez | Watch | 2025-07-15 | 2025-09-22
R-021 | Weather | 15-day heat wave stopping exterior concrete work (safety limit above 95°F) | 3-Medium | 2-Minor |  |  | Shift concrete pours to night shift; provide cooling stations; use retarding admixtures | Mike Torres | Open | 2025-09-16 | 2026-01-17
R-022 | Schedule | Steel erection sequencing conflict with precast panel installation on west facade | 3-Medium | 3-Moderate |  |  | 4D BIM model to coordinate sequencing; weekly logistics coordination meetings | Mike Torres | Open | 2025-10-03 | 2026-03-21
R-023 | Safety | Un marked underground utility line puncture during site grading | 2-Low | 5-Critical |  |  | One-call utility locate required 72 hours before any excavation; hand-dig probe zones | David Park | Mitigated | 2025-10-14 | 2026-03-20
R-024 | Procurement | Payment dispute with concrete supplier delaying all pours for 10 days | 2-Low | 4-Major |  |  | Process invoices within 5 business days; maintain 30-day reserve to cover disputes | Lisa Patel | Mitigated | 2025-06-25 | 2025-10-30
R-025 | Design | Fire protection sprinkler system tie-in requires shutdown of existing main | 2-Low | 3-Moderate |  |  | Schedule tie-in during off-hours; stage backup fire watch crew; coordinate with fire marshal | Rachel Kim | Open | 2025-06-26 | 2025-08-05
R-026 | Weather | Access road erosion after heavy rain blocking material deliveries to site | 2-Low | 3-Moderate |  |  | Install gravel reinforcement on access road; grade drainage swales; maintain emergency detour route | Mike Torres | Open | 2026-03-01 | 2026-05-12
R-027 | Procurement | Architectural precast panels not matching approved mock-up color and texture | 3-Medium | 3-Moderate |  |  | Require full-scale mock-up approval before production; reserve rejection right | Sarah Chen | Open | 2025-07-25 | 2025-08-29
R-028 | Design | Retaining wall design incomplete — geotechnical report lacked soil cohesion data | 2-Low | 4-Major |  |  | Enforce 100% design review milestone; require geotechnical sign-off before wall construction | Rachel Kim | Mitigated | 2025-12-22 | 2026-06-15
R-029 | Safety | Site security breach — theft of copper wiring from MEP laydown area | 3-Medium | 2-Minor |  |  | 24/7 security guard; fenced laydown yard with motion lights; material inventory daily | David Park | Open | 2025-09-04 | 2025-11-03
R-030 | Budget | Premium-time labor costs for weekend pours to recover 6-week schedule delay | 4-High | 3-Moderate |  |  | Track recovery schedule weekly; cap overtime at 10% of direct labor; pursue EOT from owner | Lisa Patel | Open | 2025-06-11 | 2025-10-31

## Summary
Risk Level Summary
Risk Level | Count | Percentage
Critical
High
Medium
Low
Total
Risk Category Summary
Category | Count | Percentage
Schedule
Budget
Safety
Design
Procurement
Labor
Weather
Logistics
Total