## Action Items
AI-# | Meeting Source | Description | Owner | Due Date | Status | Priority | Notes | Days Since Assigned
AI-001 | OAC | Submit revised foundation drawings to structural engineer for review | David Chen | 2026-06-15 | In Progress | High | Awaiting feedback from engineer; follow up Thursday
AI-002 | Owner Mtg | Obtain city building permit revision for south elevation change order | Maria Santos | 2026-06-25 | Open | Critical | Permit fees approved; application ready to submit
AI-003 | Field Walk | Resolve water intrusion at SW corner of basement — waterproofing detail missing | Tom Bradley | 2026-06-05 | Overdue | Critical | Subcontractor to provide repair quote by EOD
AI-004 | Design Review | Update MEP coordination drawings to reflect relocated ductwork in riser B | Lisa Nguyen | 2026-07-01 | Open | Medium | Structural clash identified; BIM coordination in progress
AI-005 | Subcontractor Mtg | Confirm steel delivery schedule for structural frame — verify mill lead times | Kevin O'Brien | 2026-06-10 | Completed | High | Delivery confirmed for June 12; updated schedule distributed
AI-006 | Internal | Approve glazing mock-up panel and sign off for production | Emily Park | 2026-06-03 | In Progress | High | Coordinating with design team
AI-007 | Field Walk | Coordinate glazing installation schedule with owner | Maria Santos | 2026-06-06 | Completed | High | Needs follow-up this week
AI-008 | Owner Mtg | Prepare HVAC change order documentation for engineer approval | Emily Park | 2026-04-14 | Deferred | Medium | In progress - awaiting update
AI-009 | Design Review | Conduct plumbing pre-installation meeting with consultant team | Carlos Rivera | 2026-04-17 | Open | Critical | Waiting on external vendor
AI-010 | OAC | Coordinate architectural installation schedule with city building dept | Kevin O'Brien | 2026-04-18 | Overdue | Low | Needs follow-up this week
AI-011 | Design Review | Verify architectural shop drawings against contract specifications | Sarah Miller | 2026-05-09 | In Progress | Low | Waiting on external vendor
AI-012 | Field Walk | Approve civil mock-up panel and sign off for production | Jake Thompson | 2026-04-18 | Open | High | In progress - awaiting update
AI-013 | Owner Mtg | Review steel subcontractor proposal and negotiate terms | Sarah Miller | 2026-06-04 | Deferred | High | Needs follow-up this week
AI-014 | Subcontractor Mtg | Schedule plumbing inspection with city building department | Emily Park | 2026-05-17 | In Progress | High | Needs follow-up this week
AI-015 | Internal | Expedite MEP material submittal for architect approval | Kevin O'Brien | 2026-06-03 | Deferred | Medium | Escalate if not resolved by Friday
AI-016 | OAC | Resolve plumbing RFI submitted by city building dept | Emily Park | 2026-04-15 | Deferred | High | Waiting on external vendor
AI-017 | Field Walk | Update site submittal log and track outstanding items | Jake Thompson | 2026-04-23 | Deferred | Medium | Budget impact under review
AI-018 | Owner Mtg | Coordinate MEP installation schedule with city building dept | Lisa Nguyen | 2026-04-19 | In Progress | Low | On track for deadline
AI-019 | Internal | Review millwork subcontractor proposal and negotiate terms | Lisa Nguyen | 2026-04-26 | Deferred | Low | Coordinating with design team
AI-020 | OAC | Review MEP subcontractor proposal and negotiate terms | David Chen | 2026-05-29 | In Progress | Medium | Budget impact under review
AI-021 | Subcontractor Mtg | Deliver fire protection O&M manuals and training documentation | Jake Thompson | 2026-05-21 | Open | Critical | Needs follow-up this week
AI-022 | Field Walk | Distribute electrical meeting minutes and track action items | Jake Thompson | 2026-05-08 | Open | Low | Needs follow-up this week
AI-023 | Design Review | Approve steel mock-up panel and sign off for production | Rachel Kim | 2026-06-01 | Overdue | Low | Escalate if not resolved by Friday
AI-024 | Subcontractor Mtg | Deliver architectural O&M manuals and training documentation | Jake Thompson | 2026-05-15 | Deferred | Low
AI-025 | Owner Mtg | Expedite fire protection material submittal for owner approval | Emily Park | 2026-05-15 | Deferred | Medium | In progress - awaiting update
AI-026 | Subcontractor Mtg | Confirm steel equipment lead times and update procurement | Emily Park | 2026-05-06 | In Progress | High | Subcontractor to provide ETA
AI-027 | Field Walk | Verify plumbing shop drawings against contract specifications | David Chen | 2026-04-22 | In Progress | High | Escalate if not resolved by Friday
AI-028 | OAC | Submit revised curtain wall drawings for architect review | Kevin O'Brien | 2026-04-27 | In Progress | Medium | Documentation filed pending review
AI-029 | Design Review | Submit revised electrical drawings for architect review | Rachel Kim | 2026-04-23 | Open | Critical | On track for deadline
AI-030 | Subcontractor Mtg | Deliver curtain wall O&M manuals and training documentation | David Chen | 2026-05-03 | Deferred | High | Subcontractor to provide ETA
AI-031 | Owner Mtg | Coordinate roofing installation schedule with city building dept | Kevin O'Brien | 2026-04-26 | Completed | High | Subcontractor to provide ETA
AI-032 | Design Review | Prepare HVAC change order documentation for subcontractor approval | Sarah Miller | 2026-04-16 | Overdue | Low | In progress - awaiting update
AI-033 | Internal | Confirm fire protection equipment lead times and update procurement | Jake Thompson | 2026-05-29 | In Progress | High | Coordinating with design team
AI-034 | Owner Mtg | Expedite concrete material submittal for city building dept approval | Tom Bradley | 2026-05-12 | Open | High | Documentation filed pending review
AI-035 | Internal | Resolve fire protection RFI submitted by engineer | David Chen | 2026-04-30 | Deferred | Medium | Needs follow-up this week
AI-036 | Internal | Deliver steel O&M manuals and training documentation | Tom Bradley | 2026-04-21 | Open | High | On track for deadline
AI-037 | Field Walk | Resolve millwork RFI submitted by consultant | Sarah Miller | 2026-06-04 | Deferred | Critical
AI-038 | Field Walk | Distribute fire protection meeting minutes and track action items | Sarah Miller | 2026-05-29 | Open | Medium | Documentation filed pending review
AI-039 | Design Review | Deliver structural O&M manuals and training documentation | Rachel Kim | 2026-05-13 | Overdue | High | Escalate if not resolved by Friday
AI-040 | Design Review | Coordinate glazing installation schedule with engineer | Lisa Nguyen | 2026-05-25 | Deferred | High | Escalate if not resolved by Friday
AI-041 | OAC | Issue MEP notice to proceed for owner scope | Carlos Rivera | 2026-05-31 | Open | Critical | Needs follow-up this week
AI-042 | Internal | Distribute roofing meeting minutes and track action items | Maria Santos | 2026-04-13 | Completed | Critical | Coordinating with design team
AI-043 | Owner Mtg | Flag architectural concealed conditions discovered during architect | David Chen | 2026-05-26 | Overdue | Low
AI-044 | Internal | Expedite architectural material submittal for engineer approval | Emily Park | 2026-04-30 | Deferred | High | Budget impact under review
AI-045 | Subcontractor Mtg | Review architectural subcontractor proposal and negotiate terms | Emily Park | 2026-05-14 | Completed | High | Needs follow-up this week
AI-046 | Field Walk | Prepare electrical change order documentation for GC approval | Tom Bradley | 2026-04-28 | Completed | Medium | Documentation filed pending review
AI-047 | Design Review | Deliver electrical O&M manuals and training documentation | Maria Santos | 2026-05-15 | Overdue | Medium | Escalate if not resolved by Friday
AI-048 | Design Review | Approve roofing mock-up panel and sign off for production | Maria Santos | 2026-04-29 | In Progress | Medium | Subcontractor to provide ETA
AI-049 | OAC | Verify fire protection layout on site before city building dept commences | Jake Thompson | 2026-05-19 | Open | Medium
AI-050 | Internal | Resolve plumbing RFI submitted by subcontractor | Lisa Nguyen | 2026-04-13 | Completed | Medium | Waiting on external vendor
Formulas:
Days Since Assigned = IF([Due Date]="","",TODAY()-[Due Date])

## Summary
Metric | Category | Count
By Status
Open
In Progress
Completed
Overdue
Deferred
Total
By Priority
Low
Medium
High
Critical
Total
By Owner
Jake Thompson
Maria Santos
David Chen
Sarah Miller
Tom Bradley
Lisa Nguyen
Kevin O'Brien
Rachel Kim
Carlos Rivera
Emily Park
Total