## Change Order Log
CO # | Description | Subcontractor | Status | Amount | Approved Amount | Date Submitted | Date Approved | Days to Approval | Scope Change
CO-001 | Additional concrete pour - North parking deck slab | Baker Concrete | Approved | 245000 | 232750 | 2025-03-10 | 2025-03-18 |  | Concrete
CO-002 | Revised steel beam connections - East upper concourse | Qualico Steel | Approved | 87500 | 87500 | 2025-03-12 | 2025-03-22 |  | Steel
CO-003 | Underground utility relocation - West entry road | A-1 All Florida | Pending | 124300 | 0 | 2025-03-15 |  |  | Utilities
CO-004 | Expanded electrical room - Main switchgear upgrade | Baker Concrete | Submitted | 68900 | 0 | 2025-03-20 |  |  | Electrical
CO-005 | Railing design change - VIP suite balcony | Qualico Steel | Rejected | 34000 | 0 | 2025-03-22 |  |  | Architectural
TOTALS

## Summary
Metric | Value
Total Change Orders
Total Amount ($)
Total Approved Amount ($)
Status Breakdown
Status: Submitted
Status: Approved
Status: Pending
Status: Rejected
Approved / Total Ratio