## OAC Agenda
Item # | Topic | Presenter | Time Allotment | Notes
1 | Safety Report |  | 5 min
2 | Schedule Review |  | 10 min
3 | Budget Update |  | 10 min
4 | Change Order Status |  | 10 min
5 | RFI/Submittal Status |  | 10 min
6 | Field Observations |  | 10 min
7 | Quality Control |  | 5 min
8 | Upcoming Milestones |  | 10 min
9 | Open Action Items |  | 10 min
10 | New Business |  | 10 min
11 | Design Issues |  | 5 min
12 | Next Meeting Date |  | 5 min

## Meeting Minutes
Meeting Date:
Project:
Location:
Attendees:
Item # | Topic | Discussion | Decision | Action Items | Owner | Due Date
1 | Safety Report
2 | Schedule Review
3 | Budget Update
4 | Change Order Status
5 | RFI/Submittal Status
6 | Field Observations
7 | Quality Control
8 | Upcoming Milestones
9 | Open Action Items
10 | New Business
11 | Design Issues
12 | Next Meeting Date

## Design Review
Drawing # | Discipline | Review Date | Reviewer | Comment | Status | Resolution
A-101 | Architectural | 2026-01-15 | John Smith | Dimension discrepancy on north elevation. | Open | Pending architect confirmation.
A-102 | Architectural | 2026-01-18 | Sarah Lee | Window schedule does not match floor plan. | Closed | Window schedule updated to match plan.
S-201 | Structural | 2026-01-20 | Mike Chen | Steel beam connection details incomplete. | Open | Awaiting engineer revision.
S-202 | Structural | 2026-01-22 | Mike Chen | Foundation plan missing column grid. | Resubmit | Grid added; resubmit for final review.
M-301 | Mechanical | 2026-01-25 | Amy Patel | Duct routing conflicts with structural beam. | Open | Coordinate with structural team.
M-302 | Mechanical | 2026-01-28 | Amy Patel | Equipment schedule missing model numbers. | Closed | Model numbers added to schedule.
E-401 | Electrical | 2026-02-01 | David Kim | Panel schedule shows incorrect voltage. | Open | Voltage correction requested from EE.
E-402 | Electrical | 2026-02-03 | David Kim | Lighting layout does not meet code req. | Resubmit | Revised layout submitted; pending AHJ review.
P-501 | Plumbing | 2026-02-05 | Linda Torres | Domestic water riser diagram incomplete. | Open | Requesting updated riser diagram.
P-502 | Plumbing | 2026-02-08 | Linda Torres | Sanitary pipe slope does not meet code. | Closed | Slope adjusted to 1/4" per foot.
FP-601 | Fire Protection | 2026-02-10 | James Brown | Sprinkler spacing exceeds NFPA 13 limits. | Open | Sprinkler layout under revision.
FP-602 | Fire Protection | 2026-02-12 | James Brown | Fire alarm devices not shown on plan. | Resubmit | Devices added; resubmit for review.
C-701 | Civil | 2026-02-15 | Rachel Ngo | Site grading conflicts with SWPPP. | Open | Grading plan being revised.
C-702 | Civil | 2026-02-18 | Rachel Ngo | Storm drain inlet spacing insufficient. | Closed | Additional inlets added per design.
L-801 | Landscape | 2026-02-20 | Tom Hardy | Plant species not suitable for climate zone. | Open | Landscape architect selecting alternatives.
L-802 | Landscape | 2026-02-22 | Tom Hardy | Irrigation layout missing valves. | Resubmit | Valve locations added; resubmit.
I-901 | Interiors | 2026-02-25 | Karen Walsh | Finish schedule conflicts with specification. | Open | Specification section being updated.
I-902 | Interiors | 2026-02-28 | Karen Walsh | Ceiling heights not coordinated with MEP. | Closed | Ceiling height revised to 10' - 0".
T-1001 | Telecom | 2026-03-02 | Scott Miller | Data outlet locations not shown. | Open | Telecom designer placing outlets.
T-1002 | Telecom | 2026-03-05 | Scott Miller | Cable tray routing conflicts with duct. | Resubmit | Alternate routing proposed; resubmit.