## Budget Tracker
Line Item | Original Budget ($) | Approved COs ($) | Revised Budget ($) | Committed ($) | Expended to Date ($) | % Complete | Remaining Budget ($) | Variance ($) | Status
General Conditions | 45000000 | 2000000 |  | 46500000 | 44800000
Site Work | 38000000 | 1500000 |  | 38200000 | 36100000
Concrete | 62000000 | 800000 |  | 61500000 | 59200000
Steel | 55000000 | 1200000 |  | 54800000 | 52500000
MEP | 120000000 | 3000000 |  | 115000000 | 108000000
Finishes | 48000000 | 1000000 |  | 46500000 | 42300000
Technology | 35000000 | 2500000 |  | 34200000 | 30100000
FF&E | 28000000 | 1800000 |  | 26800000 | 24500000
Design Fees | 18000000 | 500000 |  | 18100000 | 17600000
CM Fees | 22000000 | 600000 |  | 21800000 | 20900000
Contingency | 82000000 | 0 |  | 0 | 0
TOTAL

## Contingency Log
Draw # | Date | Description | Amount ($) | Running Balance ($) | Status | Approval Reference
1 | 2026-01-15 | Site mobilization - unexpected rock removal | 1200000 |  | Approved | CO-001
2 | 2026-02-20 | Steel price escalation - market adjustment | 2500000 |  | Approved | CO-015
3 | 2026-03-10 | MEP coordination - additional ductwork | 850000 |  | Approved | CO-028
4 | 2026-04-05 | Foundation redesign per geotechnical report | 1800000 |  | Pending | CO-042
5 | 2026-05-12 | Facade system upgrade - energy compliance | 1100000 |  | Approved | CO-056
6 | 2026-06-01 | Technology infrastructure - fiber backbone expansion | 550000 |  | Submitted | CO-071