## Punch List
Item # | Location | Trade | Description | Priority | Assignee | Date Identified | Target Date | Days Open | Status | Notes
PL-001 | Storage | HVAC | Toilet flange not secured to floor | Medium | M. Patel | 2026-01-18 | 2026-02-11 |  | Ready for Review | Inspected by N. Davis
PL-002 | Field | Electrical | Paint touch-up required on south wall | Critical | L. Chen | 2026-05-03 | 2026-05-16 |  | Open
PL-003 | Storage | Carpentry | Thermostat not communicating with BMS | Low | J. Garcia | 2026-04-27 | 2026-05-17 |  | Ready for Review
PL-004 | Exterior | Painting | Toilet flange not secured to floor | Low | R. Thompson | 2026-05-16 | 2026-06-08 |  | Rejected | Inspected by A. Kim
PL-005 | Restroom | Steel | Ceiling tile stained — replace | High | K. Johnson | 2026-05-19 | 2026-06-18 |  | Closed | Inspected by L. Chen
PL-006 | Restroom | HVAC | Sprinkler head paint overspray — clean | High | L. Chen | 2026-01-18 | 2026-02-14 |  | Closed | Inspected by N. Davis
PL-007 | Lobby | Millwork | GFCI outlet missing cover plate | Medium | R. Thompson | 2026-04-24 | 2026-05-16 |  | Closed
PL-008 | Field | Steel | Light fixture not aligned with grid | Critical | D. Williams | 2026-04-28 | 2026-05-21 |  | Closed
PL-009 | Exterior | MEP | Missing fire caulking at pipe penetration | Low | T. Brown | 2026-02-21 | 2026-03-05 |  | Open
PL-010 | Lobby | Painting | Window seal gap — apply silicone | Critical | A. Kim | 2026-01-20 | 2026-02-09 |  | In Progress
PL-011 | Lobby | Millwork | Drain cleanout plug cross-threaded | High | T. Brown | 2026-04-23 | 2026-04-30 |  | Open
PL-012 | Concourse | Millwork | Screw pops in drywall — repair and finish | Low | J. Garcia | 2026-03-12 | 2026-04-07 |  | Ready for Review | Inspected by R. Thompson
PL-013 | Lobby | MEP | Handrail bracket loose on stairway | Critical | R. Thompson | 2026-03-09 | 2026-03-16 |  | Open
PL-014 | Roof | Steel | Mirror damaged in west restroom | High | N. Davis | 2026-05-04 | 2026-05-21 |  | In Progress
PL-015 | Field | Carpentry | Floor tile cracked — replace 12×12 section | Medium | J. Garcia | 2026-06-01 | 2026-07-01 |  | Open
PL-016 | Stairwell | Plumbing | Drain cleanout plug cross-threaded | Medium | T. Brown | 2026-02-12 | 2026-02-21 |  | Closed
PL-017 | Concourse | Millwork | Drain cleanout plug cross-threaded | Medium | R. Thompson | 2026-01-26 | 2026-02-04 |  | Ready for Review
PL-018 | Field | Flooring | Paint touch-up required on south wall | Medium | K. Johnson | 2026-02-05 | 2026-02-17 |  | In Progress
PL-019 | Lobby | Millwork | Crack in concrete slab near column B-12 | Critical | T. Brown | 2026-05-07 | 2026-05-22 |  | In Progress | Inspected by S. Rodriguez
PL-020 | Exterior | Glass/Glazing | Fire damper actuator not tested | Critical | N. Davis | 2026-01-24 | 2026-02-05 |  | Ready for Review | Inspected by M. Patel
PL-021 | Exterior | Carpentry | Signage panel not level | Low | S. Rodriguez | 2026-01-17 | 2026-01-26 |  | In Progress
PL-022 | Concourse | Concrete | Sprinkler head paint overspray — clean | Low | M. Patel | 2026-06-03 | 2026-06-12 |  | Closed
PL-023 | Restroom | Carpentry | Handrail bracket loose on stairway | High | K. Johnson | 2026-02-24 | 2026-03-10 |  | Ready for Review
PL-024 | Concourse | Concrete | Sprinkler head paint overspray — clean | High | N. Davis | 2026-02-06 | 2026-02-22 |  | Open
PL-025 | Stairwell | Glass/Glazing | Caulking missing at countertop backsplash | Low | S. Rodriguez | 2026-05-05 | 2026-06-04 |  | Closed
PL-026 | Concourse | MEP | Millwork edge banding peeling on cabinet | Low | K. Johnson | 2026-04-06 | 2026-04-19 |  | Open
PL-027 | Restroom | Painting | ADA push plate missing on exit door | Critical | N. Davis | 2026-04-18 | 2026-05-05 |  | Open | Inspected by T. Brown
PL-028 | Field | Millwork | Roof membrane patched — verify watertight | Low | K. Johnson | 2026-05-25 | 2026-06-06 |  | Closed | Inspected by K. Johnson
PL-029 | MEP Room | Carpentry | Expansion joint cover loose | High | L. Chen | 2026-03-07 | 2026-04-02 |  | Closed
PL-030 | Suite | Plumbing | Crack in concrete slab near column B-12 | Medium | R. Thompson | 2026-05-15 | 2026-05-25 |  | Open | Inspected by R. Thompson
PL-031 | Concourse | General | Screw pops in drywall — repair and finish | Critical | D. Williams | 2026-05-25 | 2026-06-10 |  | Rejected | Inspected by R. Thompson
PL-032 | Roof | Finish | Screw pops in drywall — repair and finish | Critical | N. Davis | 2026-01-22 | 2026-02-06 |  | Open
PL-033 | Restroom | Flooring | Corner guard adhesive failing | Medium | T. Brown | 2026-05-30 | 2026-06-25 |  | Closed | Inspected by A. Kim
PL-034 | Lobby | Steel | Fire damper actuator not tested | Low | K. Johnson | 2026-03-28 | 2026-04-24 |  | Ready for Review
PL-035 | Exterior | Glass/Glazing | Toilet flange not secured to floor | Critical | K. Johnson | 2026-05-27 | 2026-06-10 |  | In Progress | Inspected by R. Thompson
PL-036 | Suite | Flooring | Corner guard adhesive failing | Low | D. Williams | 2026-05-24 | 2026-06-23 |  | Ready for Review | Inspected by K. Johnson
PL-037 | Field | Carpentry | Floor tile cracked — replace 12×12 section | Critical | D. Williams | 2026-03-21 | 2026-04-13 |  | Open
PL-038 | Restroom | HVAC | Screw pops in drywall — repair and finish | Low | S. Rodriguez | 2026-04-14 | 2026-04-28 |  | Open | Inspected by T. Brown
PL-039 | Lobby | MEP | Sprinkler head paint overspray — clean | Low | R. Thompson | 2026-01-23 | 2026-02-18 |  | Closed
PL-040 | Concourse | Carpentry | Corner guard adhesive failing | Low | K. Johnson | 2026-01-21 | 2026-02-08 |  | Open | Inspected by N. Davis
PL-041 | Roof | General | Rainwater downspout extension missing | Medium | K. Johnson | 2026-05-04 | 2026-05-11 |  | Ready for Review
PL-042 | Suite | Steel | Sprinkler head paint overspray — clean | Critical | D. Williams | 2026-04-25 | 2026-05-07 |  | Open | Inspected by A. Kim
PL-043 | Concourse | Carpentry | Door closer speed set too fast | Low | M. Patel | 2026-02-20 | 2026-03-21 |  | Rejected
PL-044 | Suite | Concrete | Toilet flange not secured to floor | High | J. Garcia | 2026-02-17 | 2026-03-07 |  | Open
PL-045 | Field | Plumbing | Window seal gap — apply silicone | High | N. Davis | 2026-04-10 | 2026-05-02 |  | Closed
PL-046 | Lobby | Glass/Glazing | Baseboard gap exceeds 1/8" at joint | Low | L. Chen | 2026-03-03 | 2026-03-24 |  | Closed
PL-047 | Suite | MEP | Handrail bracket loose on stairway | Medium | A. Kim | 2026-02-05 | 2026-02-27 |  | In Progress
PL-048 | Field | Carpentry | Thermostat not communicating with BMS | Low | K. Johnson | 2026-04-27 | 2026-05-25 |  | Rejected
PL-049 | Roof | Finish | Ceiling tile stained — replace | Low | M. Patel | 2026-02-07 | 2026-03-01 |  | Ready for Review | Inspected by J. Garcia
PL-050 | Roof | General | Toilet flange not secured to floor | Low | S. Rodriguez | 2026-03-09 | 2026-04-07 |  | Closed
PL-051 | Storage | Flooring | Mirror damaged in west restroom | Critical | T. Brown | 2026-05-31 | 2026-06-22 |  | Open
PL-052 | Exterior | MEP | Missing fire caulking at pipe penetration | Medium | K. Johnson | 2026-04-05 | 2026-04-24 |  | In Progress
PL-053 | Suite | Electrical | Roof membrane patched — verify watertight | Critical | N. Davis | 2026-05-11 | 2026-05-20 |  | Closed
PL-054 | Stairwell | Steel | Crack in concrete slab near column B-12 | Critical | K. Johnson | 2026-04-22 | 2026-05-13 |  | In Progress | Inspected by T. Brown
PL-055 | Stairwell | Finish | HVAC duct insulation gap at return plenum | Critical | N. Davis | 2026-04-25 | 2026-05-05 |  | Open | Inspected by K. Johnson
PL-056 | Field | Flooring | Mirror damaged in west restroom | High | A. Kim | 2026-04-14 | 2026-05-02 |  | Ready for Review | Inspected by M. Patel
PL-057 | Storage | HVAC | Door closer speed set too fast | Low | N. Davis | 2026-01-18 | 2026-02-08 |  | Closed
PL-058 | Stairwell | HVAC | Door closer speed set too fast | Low | J. Garcia | 2026-02-25 | 2026-03-17 |  | Closed
PL-059 | Field | Plumbing | EMT conduit support clamp missing | Low | L. Chen | 2026-04-15 | 2026-04-28 |  | In Progress
PL-060 | Storage | Finish | Light fixture not aligned with grid | Medium | A. Kim | 2026-05-18 | 2026-06-02 |  | In Progress
PL-061 | Restroom | HVAC | Thermostat not communicating with BMS | Critical | D. Williams | 2026-01-18 | 2026-01-25 |  | Rejected
PL-062 | Roof | Plumbing | Expansion joint cover loose | Critical | A. Kim | 2026-05-18 | 2026-05-25 |  | In Progress | Inspected by T. Brown
PL-063 | Roof | MEP | Ceiling tile stained — replace | High | A. Kim | 2026-05-02 | 2026-05-10 |  | Ready for Review | Inspected by K. Johnson
PL-064 | Storage | Finish | Baseboard gap exceeds 1/8" at joint | Low | J. Garcia | 2026-04-11 | 2026-05-11 |  | Closed
PL-065 | Restroom | Glass/Glazing | Window seal gap — apply silicone | High | T. Brown | 2026-03-12 | 2026-04-02 |  | Open
PL-066 | Concourse | Carpentry | Light fixture not aligned with grid | Critical | M. Patel | 2026-04-27 | 2026-05-07 |  | Closed | Inspected by M. Patel
PL-067 | MEP Room | Finish | Crack in concrete slab near column B-12 | Critical | J. Garcia | 2026-01-18 | 2026-01-29 |  | Closed
PL-068 | Field | General | Floor tile cracked — replace 12×12 section | Medium | D. Williams | 2026-01-25 | 2026-02-05 |  | Closed | Inspected by J. Garcia
PL-069 | Storage | Electrical | Mirror damaged in west restroom | Medium | K. Johnson | 2026-01-29 | 2026-02-26 |  | Closed | Inspected by T. Brown
PL-070 | Lobby | MEP | Missing fire caulking at pipe penetration | High | A. Kim | 2026-04-12 | 2026-04-20 |  | Open
PL-071 | Roof | Steel | GFCI outlet missing cover plate | Low | T. Brown | 2026-06-06 | 2026-07-02 |  | Open | Inspected by D. Williams
PL-072 | Stairwell | Carpentry | Toilet flange not secured to floor | Low | D. Williams | 2026-06-02 | 2026-06-19 |  | Open
PL-073 | Stairwell | General | Ceiling tile stained — replace | Medium | J. Garcia | 2026-04-28 | 2026-05-14 |  | Rejected
PL-074 | Exterior | Finish | Light fixture not aligned with grid | Critical | K. Johnson | 2026-06-04 | 2026-06-29 |  | Open
PL-075 | Concourse | HVAC | Mirror damaged in west restroom | Low | T. Brown | 2026-05-04 | 2026-05-23 |  | Rejected | Inspected by R. Thompson
PL-076 | Lobby | Finish | Floor tile cracked — replace 12×12 section | Medium | S. Rodriguez | 2026-03-09 | 2026-04-03 |  | In Progress
PL-077 | Lobby | Electrical | Screw pops in drywall — repair and finish | Medium | T. Brown | 2026-05-30 | 2026-06-16 |  | Open | Inspected by D. Williams
PL-078 | Exterior | General | Window seal gap — apply silicone | Low | L. Chen | 2026-04-09 | 2026-04-27 |  | In Progress
PL-079 | Field | Millwork | Door frame not plumb — shim and adjust | Critical | N. Davis | 2026-03-26 | 2026-04-15 |  | In Progress | Inspected by K. Johnson
PL-080 | Storage | Concrete | HVAC duct insulation gap at return plenum | Low | R. Thompson | 2026-06-07 | 2026-06-24 |  | Closed
PL-081 | Lobby | Finish | Mirror damaged in west restroom | Low | D. Williams | 2026-02-21 | 2026-03-03 |  | In Progress
PL-082 | Lobby | Concrete | Drain cleanout plug cross-threaded | Medium | A. Kim | 2026-03-04 | 2026-03-22 |  | Open
PL-083 | Concourse | General | Expansion joint cover loose | Low | T. Brown | 2026-03-02 | 2026-04-01 |  | Open
PL-084 | Stairwell | Glass/Glazing | Screw pops in drywall — repair and finish | High | L. Chen | 2026-02-20 | 2026-03-01 |  | Closed | Inspected by A. Kim
PL-085 | Storage | HVAC | Handrail bracket loose on stairway | Critical | M. Patel | 2026-02-13 | 2026-02-25 |  | Ready for Review | Inspected by D. Williams
PL-086 | Stairwell | Electrical | Fire damper actuator not tested | High | N. Davis | 2026-03-10 | 2026-03-30 |  | Closed
PL-087 | Stairwell | Carpentry | Drain cleanout plug cross-threaded | Low | T. Brown | 2026-01-24 | 2026-02-11 |  | Closed
PL-088 | Restroom | HVAC | Millwork edge banding peeling on cabinet | Medium | K. Johnson | 2026-02-21 | 2026-03-05 |  | Open
PL-089 | MEP Room | Painting | Baseboard gap exceeds 1/8" at joint | High | J. Garcia | 2026-05-19 | 2026-06-02 |  | Open | Inspected by S. Rodriguez
PL-090 | Suite | HVAC | Curb angle not anchored per detail | Medium | S. Rodriguez | 2026-04-08 | 2026-04-27 |  | Closed
PL-091 | Roof | Electrical | Missing fire caulking at pipe penetration | Critical | A. Kim | 2026-04-03 | 2026-04-17 |  | Open
PL-092 | Lobby | MEP | Light fixture not aligned with grid | Critical | M. Patel | 2026-04-27 | 2026-05-27 |  | Open | Inspected by A. Kim
PL-093 | Lobby | Glass/Glazing | Crack in concrete slab near column B-12 | High | M. Patel | 2026-03-23 | 2026-04-11 |  | Open | Inspected by S. Rodriguez
PL-094 | Storage | Steel | Expansion joint cover loose | Medium | T. Brown | 2026-03-26 | 2026-04-12 |  | Open
PL-095 | Exterior | Painting | Baseboard gap exceeds 1/8" at joint | Medium | T. Brown | 2026-02-22 | 2026-03-02 |  | Open
PL-096 | MEP Room | Electrical | Thermostat not communicating with BMS | Critical | A. Kim | 2026-04-12 | 2026-05-01 |  | Ready for Review
PL-097 | Lobby | Carpentry | Expansion joint cover loose | Low | A. Kim | 2026-03-20 | 2026-04-13 |  | In Progress | Inspected by S. Rodriguez
PL-098 | Stairwell | Steel | Curb angle not anchored per detail | Critical | T. Brown | 2026-04-05 | 2026-05-05 |  | Closed
PL-099 | Field | Finish | Mirror damaged in west restroom | Low | A. Kim | 2026-05-12 | 2026-06-09 |  | Closed | Inspected by D. Williams
PL-100 | Restroom | General | Curb angle not anchored per detail | High | N. Davis | 2026-03-06 | 2026-03-27 |  | Rejected
PL-101 | Concourse | Concrete | Caulking missing at countertop backsplash | Low | A. Kim | 2026-01-19 | 2026-02-03 |  | Closed
PL-102 | Lobby | Electrical | Millwork edge banding peeling on cabinet | Low | A. Kim | 2026-02-18 | 2026-03-07 |  | In Progress
PL-103 | Stairwell | Plumbing | Toilet flange not secured to floor | Low | J. Garcia | 2026-03-16 | 2026-03-25 |  | Closed | Inspected by N. Davis
PL-104 | Field | General | Light fixture not aligned with grid | Critical | L. Chen | 2026-04-28 | 2026-05-15 |  | Open
PL-105 | Roof | Glass/Glazing | EMT conduit support clamp missing | High | T. Brown | 2026-05-26 | 2026-06-02 |  | In Progress
PL-106 | Roof | Plumbing | Door closer speed set too fast | High | R. Thompson | 2026-04-10 | 2026-05-03 |  | Open | Inspected by N. Davis
PL-107 | Lobby | Finish | Rainwater downspout extension missing | High | T. Brown | 2026-02-17 | 2026-03-06 |  | In Progress
PL-108 | Suite | Electrical | Drain cleanout plug cross-threaded | Critical | M. Patel | 2026-02-14 | 2026-03-14 |  | Open
PL-109 | Stairwell | Painting | Sprinkler head paint overspray — clean | Low | A. Kim | 2026-05-18 | 2026-06-04 |  | In Progress | Inspected by S. Rodriguez
PL-110 | Concourse | Carpentry | Roof membrane patched — verify watertight | High | N. Davis | 2026-03-03 | 2026-03-18 |  | In Progress
PL-111 | Exterior | Glass/Glazing | Fire damper actuator not tested | Critical | T. Brown | 2026-03-23 | 2026-04-04 |  | Ready for Review
PL-112 | Roof | Glass/Glazing | Corner guard adhesive failing | Low | N. Davis | 2026-02-25 | 2026-03-17 |  | Closed | Inspected by D. Williams
PL-113 | Storage | Concrete | Roof membrane patched — verify watertight | High | J. Garcia | 2026-03-25 | 2026-04-09 |  | Open | Inspected by J. Garcia
PL-114 | Suite | MEP | Baseboard gap exceeds 1/8" at joint | Medium | T. Brown | 2026-04-21 | 2026-05-09 |  | Open
PL-115 | Roof | Painting | Caulking missing at countertop backsplash | Medium | N. Davis | 2026-05-15 | 2026-06-09 |  | Closed
PL-116 | Field | Carpentry | Crack in concrete slab near column B-12 | High | M. Patel | 2026-03-13 | 2026-03-28 |  | Closed
PL-117 | Restroom | Carpentry | Thermostat not communicating with BMS | Critical | M. Patel | 2026-04-16 | 2026-05-11 |  | Open | Inspected by S. Rodriguez
PL-118 | Stairwell | Concrete | Drain cleanout plug cross-threaded | High | L. Chen | 2026-04-30 | 2026-05-08 |  | Open | Inspected by D. Williams
PL-119 | Restroom | HVAC | GFCI outlet missing cover plate | Medium | K. Johnson | 2026-04-03 | 2026-04-27 |  | Rejected
PL-120 | Roof | Concrete | Expansion joint cover loose | Low | A. Kim | 2026-04-18 | 2026-05-03 |  | Closed | Inspected by T. Brown
PL-121 | Storage | Painting | Drain cleanout plug cross-threaded | Critical | N. Davis | 2026-06-07 | 2026-07-04 |  | Ready for Review | Inspected by A. Kim
PL-122 | Restroom | Carpentry | Door frame not plumb — shim and adjust | Low | J. Garcia | 2026-03-13 | 2026-04-03 |  | Closed
PL-123 | Stairwell | Millwork | Toilet flange not secured to floor | Low | M. Patel | 2026-04-10 | 2026-04-18 |  | Closed | Inspected by T. Brown
PL-124 | Stairwell | General | Door frame not plumb — shim and adjust | Critical | J. Garcia | 2026-01-27 | 2026-02-12 |  | In Progress
PL-125 | Storage | Carpentry | Crack in concrete slab near column B-12 | High | N. Davis | 2026-02-02 | 2026-02-14 |  | Ready for Review | Inspected by D. Williams
PL-126 | Storage | Concrete | Caulking missing at countertop backsplash | Critical | M. Patel | 2026-05-31 | 2026-06-23 |  | In Progress
PL-127 | Roof | Millwork | Signage panel not level | Medium | A. Kim | 2026-03-31 | 2026-04-09 |  | Open | Inspected by D. Williams
PL-128 | Restroom | Carpentry | EMT conduit support clamp missing | Medium | L. Chen | 2026-05-15 | 2026-06-08 |  | Closed
PL-129 | Field | Finish | Door closer speed set too fast | Low | J. Garcia | 2026-05-27 | 2026-06-18 |  | Open | Inspected by L. Chen
PL-130 | Exterior | Steel | Fire damper actuator not tested | Medium | N. Davis | 2026-03-18 | 2026-04-16 |  | Closed | Inspected by M. Patel
PL-131 | Restroom | Millwork | Rainwater downspout extension missing | Critical | D. Williams | 2026-02-26 | 2026-03-09 |  | Ready for Review
PL-132 | Concourse | Painting | Thermostat not communicating with BMS | Critical | D. Williams | 2026-05-15 | 2026-06-13 |  | Open | Inspected by T. Brown
PL-133 | Restroom | Finish | Expansion joint cover loose | Medium | M. Patel | 2026-03-10 | 2026-03-19 |  | Open | Inspected by J. Garcia
PL-134 | Field | HVAC | Light fixture not aligned with grid | High | A. Kim | 2026-06-06 | 2026-06-16 |  | Open
PL-135 | Roof | Millwork | Curb angle not anchored per detail | Low | T. Brown | 2026-03-07 | 2026-03-15 |  | In Progress
PL-136 | Exterior | HVAC | Curb angle not anchored per detail | Medium | S. Rodriguez | 2026-06-07 | 2026-06-23 |  | Ready for Review | Inspected by N. Davis
PL-137 | Suite | Millwork | Rainwater downspout extension missing | Medium | S. Rodriguez | 2026-05-15 | 2026-06-11 |  | In Progress | Inspected by D. Williams
PL-138 | Suite | HVAC | Caulking missing at countertop backsplash | Medium | T. Brown | 2026-03-13 | 2026-03-28 |  | Open
PL-139 | Stairwell | Glass/Glazing | Door frame not plumb — shim and adjust | Low | N. Davis | 2026-02-03 | 2026-03-05 |  | Closed | Inspected by J. Garcia
PL-140 | Concourse | Steel | Caulking missing at countertop backsplash | Critical | L. Chen | 2026-05-07 | 2026-05-26 |  | Open | Inspected by D. Williams
PL-141 | Exterior | Electrical | Roof membrane patched — verify watertight | Low | N. Davis | 2026-02-22 | 2026-03-10 |  | Closed | Inspected by J. Garcia
PL-142 | Roof | Finish | Paint touch-up required on south wall | Low | A. Kim | 2026-02-18 | 2026-03-03 |  | Open | Inspected by R. Thompson
PL-143 | Storage | HVAC | Door closer speed set too fast | Low | R. Thompson | 2026-05-23 | 2026-06-02 |  | In Progress | Inspected by M. Patel
PL-144 | Restroom | Steel | Crack in concrete slab near column B-12 | Medium | K. Johnson | 2026-06-03 | 2026-06-21 |  | In Progress
PL-145 | MEP Room | Finish | Sprinkler head paint overspray — clean | Low | S. Rodriguez | 2026-05-29 | 2026-06-09 |  | Ready for Review | Inspected by D. Williams
PL-146 | Roof | Plumbing | ADA push plate missing on exit door | Medium | A. Kim | 2026-03-20 | 2026-03-28 |  | Open
PL-147 | Roof | General | Window seal gap — apply silicone | High | K. Johnson | 2026-04-27 | 2026-05-09 |  | In Progress
PL-148 | MEP Room | HVAC | Door frame not plumb — shim and adjust | Medium | K. Johnson | 2026-04-17 | 2026-05-13 |  | In Progress | Inspected by K. Johnson
PL-149 | Concourse | MEP | Light fixture not aligned with grid | High | R. Thompson | 2026-05-05 | 2026-05-13 |  | Closed
PL-150 | Stairwell | Finish | Expansion joint cover loose | High | D. Williams | 2026-02-16 | 2026-03-10 |  | Closed | Inspected by S. Rodriguez
PL-151 | Restroom | HVAC | Caulking missing at countertop backsplash | High | D. Williams | 2026-05-20 | 2026-06-11 |  | Closed
PL-152 | Exterior | Steel | Curb angle not anchored per detail | High | S. Rodriguez | 2026-02-01 | 2026-02-16 |  | Rejected | Inspected by K. Johnson
PL-153 | Storage | HVAC | Roof membrane patched — verify watertight | Critical | L. Chen | 2026-03-24 | 2026-04-07 |  | Ready for Review
PL-154 | Roof | MEP | Fire damper actuator not tested | Medium | K. Johnson | 2026-04-12 | 2026-05-08 |  | In Progress | Inspected by A. Kim
PL-155 | MEP Room | Millwork | Ceiling tile stained — replace | High | N. Davis | 2026-02-23 | 2026-03-24 |  | Closed
PL-156 | Concourse | Painting | GFCI outlet missing cover plate | High | L. Chen | 2026-03-20 | 2026-04-08 |  | Rejected
PL-157 | Lobby | Plumbing | Light fixture not aligned with grid | Low | T. Brown | 2026-04-02 | 2026-04-09 |  | In Progress | Inspected by N. Davis
PL-158 | Storage | Carpentry | Sprinkler head paint overspray — clean | Medium | D. Williams | 2026-04-06 | 2026-05-05 |  | Open
PL-159 | Exterior | MEP | Baseboard gap exceeds 1/8" at joint | Low | K. Johnson | 2026-05-27 | 2026-06-09 |  | In Progress | Inspected by R. Thompson
PL-160 | Suite | HVAC | EMT conduit support clamp missing | Critical | D. Williams | 2026-03-31 | 2026-04-24 |  | In Progress
PL-161 | Stairwell | Finish | Rainwater downspout extension missing | Critical | N. Davis | 2026-03-30 | 2026-04-20 |  | Open
PL-162 | Lobby | Flooring | Expansion joint cover loose | Medium | A. Kim | 2026-03-20 | 2026-04-19 |  | Closed | Inspected by R. Thompson
PL-163 | Field | MEP | Light fixture not aligned with grid | Low | T. Brown | 2026-03-25 | 2026-04-14 |  | In Progress | Inspected by R. Thompson
PL-164 | MEP Room | Carpentry | Door closer speed set too fast | Low | M. Patel | 2026-05-28 | 2026-06-26 |  | Rejected | Inspected by T. Brown
PL-165 | Restroom | HVAC | Window seal gap — apply silicone | Critical | R. Thompson | 2026-06-04 | 2026-06-12 |  | Open
PL-166 | Stairwell | MEP | Sprinkler head paint overspray — clean | Medium | M. Patel | 2026-06-01 | 2026-06-27 |  | Open
PL-167 | Roof | MEP | Mirror damaged in west restroom | High | M. Patel | 2026-01-25 | 2026-02-18 |  | Closed | Inspected by R. Thompson
PL-168 | Stairwell | MEP | Crack in concrete slab near column B-12 | Medium | T. Brown | 2026-02-18 | 2026-03-01 |  | Open
PL-169 | MEP Room | Flooring | Caulking missing at countertop backsplash | High | T. Brown | 2026-05-21 | 2026-06-07 |  | In Progress | Inspected by D. Williams
PL-170 | Lobby | Flooring | Paint touch-up required on south wall | Low | M. Patel | 2026-05-25 | 2026-06-23 |  | Open
PL-171 | Field | General | Caulking missing at countertop backsplash | High | T. Brown | 2026-04-08 | 2026-05-07 |  | Open
PL-172 | Exterior | Glass/Glazing | EMT conduit support clamp missing | High | M. Patel | 2026-03-20 | 2026-04-04 |  | Closed | Inspected by D. Williams
PL-173 | Concourse | Steel | Millwork edge banding peeling on cabinet | Low | T. Brown | 2026-03-12 | 2026-03-28 |  | Closed | Inspected by D. Williams
PL-174 | Stairwell | Steel | Millwork edge banding peeling on cabinet | High | K. Johnson | 2026-01-16 | 2026-02-11 |  | Closed
PL-175 | Concourse | HVAC | HVAC duct insulation gap at return plenum | Medium | R. Thompson | 2026-04-06 | 2026-04-27 |  | Ready for Review | Inspected by K. Johnson
PL-176 | Concourse | Glass/Glazing | Light fixture not aligned with grid | Low | R. Thompson | 2026-02-15 | 2026-03-17 |  | Closed | Inspected by A. Kim
PL-177 | Roof | Steel | Ceiling tile stained — replace | Low | R. Thompson | 2026-04-25 | 2026-05-13 |  | Open
PL-178 | Concourse | General | EMT conduit support clamp missing | Critical | J. Garcia | 2026-04-02 | 2026-04-17 |  | In Progress | Inspected by M. Patel
PL-179 | Stairwell | Electrical | Handrail bracket loose on stairway | High | K. Johnson | 2026-03-21 | 2026-03-29 |  | Closed | Inspected by D. Williams
PL-180 | Restroom | Steel | Handrail bracket loose on stairway | Low | L. Chen | 2026-02-08 | 2026-02-18 |  | Open | Inspected by A. Kim
PL-181 | Lobby | Glass/Glazing | Signage panel not level | Medium | M. Patel | 2026-02-12 | 2026-02-19 |  | Closed
PL-182 | Stairwell | Steel | Baseboard gap exceeds 1/8" at joint | High | N. Davis | 2026-04-26 | 2026-05-09 |  | Closed
PL-183 | Concourse | Concrete | ADA push plate missing on exit door | Medium | T. Brown | 2026-02-27 | 2026-03-27 |  | Closed | Inspected by A. Kim
PL-184 | Concourse | Carpentry | ADA push plate missing on exit door | Low | N. Davis | 2026-03-22 | 2026-04-06 |  | Closed | Inspected by T. Brown
PL-185 | Field | Steel | Light fixture not aligned with grid | Medium | A. Kim | 2026-01-16 | 2026-02-01 |  | Open
PL-186 | MEP Room | Flooring | Curb angle not anchored per detail | High | J. Garcia | 2026-01-18 | 2026-02-04 |  | Closed | Inspected by K. Johnson
PL-187 | Stairwell | Electrical | Ceiling tile stained — replace | High | D. Williams | 2026-06-01 | 2026-06-12 |  | Open
PL-188 | Suite | Carpentry | Missing fire caulking at pipe penetration | High | K. Johnson | 2026-05-30 | 2026-06-20 |  | Closed
PL-189 | Exterior | General | Window seal gap — apply silicone | Critical | D. Williams | 2026-03-26 | 2026-04-02 |  | Closed
PL-190 | Suite | Painting | Curb angle not anchored per detail | Critical | D. Williams | 2026-05-06 | 2026-05-22 |  | Open | Inspected by L. Chen
PL-191 | Stairwell | Plumbing | Crack in concrete slab near column B-12 | High | T. Brown | 2026-05-20 | 2026-06-11 |  | Closed | Inspected by R. Thompson
PL-192 | Roof | Flooring | Door frame not plumb — shim and adjust | Medium | N. Davis | 2026-02-05 | 2026-02-27 |  | Open | Inspected by N. Davis
PL-193 | Suite | Painting | Roof membrane patched — verify watertight | High | J. Garcia | 2026-02-26 | 2026-03-15 |  | Open
PL-194 | Suite | Finish | Light fixture not aligned with grid | Medium | M. Patel | 2026-05-28 | 2026-06-14 |  | Open | Inspected by R. Thompson
PL-195 | Storage | Millwork | Rainwater downspout extension missing | Medium | L. Chen | 2026-03-27 | 2026-04-23 |  | Closed | Inspected by J. Garcia
PL-196 | Field | MEP | Floor tile cracked — replace 12×12 section | High | S. Rodriguez | 2026-02-02 | 2026-02-09 |  | Ready for Review
PL-197 | Lobby | General | Expansion joint cover loose | Low | M. Patel | 2026-03-22 | 2026-03-29 |  | Closed
PL-198 | Concourse | MEP | Baseboard gap exceeds 1/8" at joint | Medium | K. Johnson | 2026-03-14 | 2026-04-02 |  | Open
PL-199 | Stairwell | Steel | Toilet flange not secured to floor | High | L. Chen | 2026-02-12 | 2026-03-04 |  | Open | Inspected by D. Williams
PL-200 | Restroom | General | Curb angle not anchored per detail | High | R. Thompson | 2026-03-31 | 2026-04-19 |  | In Progress | Inspected by T. Brown
SUMMARY
Total Items
Open Items
In Progress
Ready for Review
Closed
Rejected
BY PRIORITY
Low
Medium
High
Critical
BY STATUS
Open
In Progress
Ready for Review
Closed
Rejected
Formulas:
Days Open = IF([Date Identified]="","",TODAY()-[Date Identified])

## Summary
PUNCH LIST SUMMARY REPORT
Total Items
STATUS BREAKDOWN
Open
In Progress
Ready for Review
Closed
Rejected
BY PRIORITY
Low
Medium
High
Critical
TOP TRADES
Concrete
Steel
MEP
Finish
Electrical
Plumbing
HVAC
Carpentry
Painting
Flooring
AVERAGE DAYS OPEN
Avg Days Open (Open Items)
Avg Days Open (All Items)