## Executive Summary
MFP STADIUM — WEEKLY STATUS REPORT
Project Name: | MFP Stadium
Report Date: | Monday, June 01, 2026
Report Period: | May 26 – Jun 01, 2026 (Week 22)
Project Status: | Under Construction — Phase 2
◉ OVERALL HEALTH
🟢 GREEN |  | Project is on schedule and within budget. Minor supply-chain risks being monitored.
◉ KEY MILESTONES — THIS WEEK
Milestone | Planned Date | Actual Date | Variance | Status
Concrete Foundation East Wing | 2026-05-26 | 2026-05-24 | -2 days | Complete
Structural Steel Delivery | 2026-05-28 | 2026-05-28 | 0 days | Complete
MEP Rough-In — Level 1 | 2026-05-30 | 2026-05-31 | +1 day | Complete
Roof Truss Installation | 2026-06-01 | 2026-06-01 | 0 days | Complete
Electrical Conduit — West Wing | 2026-06-02 | — | — | In Progress
◉ BUDGET SUMMARY
Original Budget | $12,500,000
Current Budget | $12,750,000
Committed | $8,920,000
Expended | $7,450,000
Remaining | $5,300,000
% Complete | 58.4%
◉ SCHEDULE SUMMARY
Planned Completion: | December 15, 2026
Forecast Completion: | December 22, 2026
Variance: | +7 days
Schedule Status: | At Risk
◉ TOP 3 ISSUES
Issue | Impact | Action |  |  | Owner | Due Date
Steel beam fabrication delay — Supplier B |  | Critical-path impact on roof truss installation; 3-day schedule slip possible |  | Expedite shipping; source alternate supplier in Phoenix |  | J. Martinez | 2026-06-05
HVAC ductwork coordination with structural |  | MEP rough-in on Level 2 blocked; idle crew cost ~$4,200/day |  | Daily BIM coordination huddle; re-sequence drywall |  | A. Patel | 2026-06-03
Concrete curing — West wing column pour |  | Cold weather slowed cure time; strength test at 85% |  | Extended curing with insulated blankets; re-test Jun 04 |  | R. Okafor | 2026-06-04

## Detailed Log
Work Package | Trade | % Complete | Planned Start | Actual Start | Planned Finish | Forecast Finish | Variance (days) | Status | Notes
Site Preparation & Demolition | Civil | 100 | 2026-01-06 | 2026-01-06 | 2026-02-14 | 2026-02-12 |  | Complete | Cleared and graded. All demo complete.
Foundation — East Wing | Concrete | 100 | 2026-02-17 | 2026-02-17 | 2026-03-28 | 2026-03-26 |  | Complete | Poured and cured. Test results passed.
Foundation — West Wing | Concrete | 100 | 2026-02-24 | 2026-02-26 | 2026-04-04 | 2026-04-07 |  | Complete | 1-day delay from cold weather; recovered.
Structural Steel — Frame | Steel | 95 | 2026-04-07 | 2026-04-07 | 2026-05-16 | 2026-05-19 |  | At Risk | Awaiting final beam delivery from Supplier B.
Roof Truss Installation | Steel | 40 | 2026-05-19 | 2026-05-21 | 2026-06-13 | 2026-06-18 |  | At Risk | Delayed by steel beam fabrication issue.
MEP Rough-In — Level 1 | MEP | 85 | 2026-05-05 | 2026-05-05 | 2026-06-05 | 2026-06-06 |  | On Track | HVAC ductwork 80% installed.
MEP Rough-In — Level 2 | MEP | 30 | 2026-05-26 | 2026-05-28 | 2026-06-19 | 2026-06-23 |  | Behind | Blocked by structural coordination; daily BIM huddle.
Electrical Conduit — East Wing | Electrical | 70 | 2026-05-12 | 2026-05-12 | 2026-06-09 | 2026-06-09 |  | On Track | On schedule. 3 crews active.
Electrical Conduit — West Wing | Electrical | 45 | 2026-05-19 | 2026-05-20 | 2026-06-16 | 2026-06-18 |  | On Track | Slight delay from conduit routing rework.
Plumbing — Core & Shell | Plumbing | 60 | 2026-05-12 | 2026-05-14 | 2026-06-16 | 2026-06-17 |  | On Track | Underslab rough-in complete.
Fire Protection — Level 1 | Fire Safety | 50 | 2026-05-26 | 2026-05-27 | 2026-06-19 | 2026-06-20 |  | On Track | Sprinkler mains installed.
Fire Protection — Level 2 | Fire Safety | 15 | 2026-06-02 | 2026-06-03 | 2026-06-26 | 2026-06-30 |  | Behind | Waiting on MEP rough-in completion.
Exterior Masonry — East | Masonry | 20 | 2026-05-26 | 2026-05-28 | 2026-07-10 | 2026-07-14 |  | Behind | Weather delays on exterior work.
Exterior Masonry — West | Masonry | 10 | 2026-06-02 | — | 2026-07-17 | 2026-07-21 |  | At Risk | Crew reassigned; start pushed.
Drywall — Interior Level 1 | Drywall | 25 | 2026-06-02 | 2026-06-03 | 2026-07-03 | 2026-07-07 |  | On Track | Framing 30% complete.
Drywall — Interior Level 2 | Drywall | 5 | 2026-06-09 | — | 2026-07-10 | 2026-07-14 |  | At Risk | Not yet started; MEP rough-in must finish first.
Painting — Level 1 | Finishes | 0 | 2026-07-07 | — | 2026-07-28 | 2026-07-30 |  | At Risk | Dependent on drywall completion.
Flooring — Concourses | Finishes | 0 | 2026-07-14 | — | 2026-08-04 | 2026-08-06 |  | At Risk | Material on order; 4-week lead time.
Elevator Installation | Vertical | 10 | 2026-05-26 | 2026-05-28 | 2026-07-28 | 2026-08-04 |  | Behind | Hoistway steel delayed; vendor behind schedule.
Commissioning — Phase 1 | Testing | 0 | 2026-08-04 | — | 2026-09-01 | 2026-09-08 |  | At Risk | Pre-commissioning checklist in progress.

## Action Items
# | Action Item | Assigned To | Notes / Status Update | Priority | Due Date | Status
1 | Expedite steel beam fabrication — Supplier B escalation | J. Martinez | Escalation call made Jun 01; awaiting revised delivery date. | High | 2026-06-05 | In Progress
2 | Resolve HVAC ductwork / structural interference on Level 2 | A. Patel | BIM coordination session scheduled Jun 03 @ 9am. | High | 2026-06-03 | In Progress
3 | Arrange concrete re-test for West Wing column | R. Okafor | Testing lab confirmed Jun 04; insulated blankets applied. | Medium | 2026-06-04 | In Progress
4 | Source alternate steel fabricator (backup for Supplier B) | J. Martinez | RFQ sent to 3 vendors; quotes due Jun 05. | High | 2026-06-07 | Open
5 | Update project schedule — incorporate MEP re-sequence | P. Simmons | Draft schedule revision ready for review. | Medium | 2026-06-04 | In Progress
6 | Submit RFI for exterior masonry material substitution | T. Chen | RFI filed with architect; response expected Jun 08. | Medium | 2026-06-08 | Open
7 | Weekly safety walk — East Wing steel erection | L. Brooks | Scheduled Friday Jun 05 @ 7am. All PPE verified. | High | 2026-06-05 | Open
8 | Approve change order #CO-014 — extra conduit runs | K. Williams | Change order submitted; budget impact ~$38k. | Medium | 2026-06-09 | Open
9 | Commissioning plan — review and sign off | D. Chang | Draft plan circulated Jun 01; feedback due Jun 08. | Low | 2026-06-10 | Open
10 | Prepare weekly progress photos & owner summary | M. Torres | Photo log compiled; summary deck draft in progress. | Low | 2026-06-02 | Complete