## Procurement Tracker
Item # | Description | Category | Quantity | Unit | Unit Price ($) | Total Price | Status | Vendor | PO # | Order Date | Expected Delivery | Actual Delivery | Lead Time (days) | Delay (days) | Install By | F/I | Notes
1 | Stadium seating - lower bowl | AV/Technology | 392 | UNIT | 11726.09 |  | Shipped | Daktronics | PO-2026-0001 | 2025-05-23 | 2025-09-26 |  |  |  | 2025-11-06 | Owner
2 | LED scoreboard main display | Furniture | 247 | LF | 17474.96 |  | Complete | American Seating | PO-2026-0002 | 2026-02-22 | 2026-03-26 | 2026-03-28 |  |  | 2026-04-29 | Vendor
3 | Concession counter equipment | OS&E | 210 | GL | 7619.02 |  | Ordered | Herman Miller | PO-2026-0003 | 2025-09-23 | 2025-10-13 |  |  |  | 2025-11-24 | GC
4 | Field turf & drainage system | OS&E | 108 | GL | 19589.21 |  | Received | Sherwin-Williams | PO-2026-0004 | 2025-03-20 | 2025-04-07 | 2025-04-03 |  |  | 2025-05-22 | Vendor
5 | Sound system - main array | Art/Decor | 126 | LF | 1593.69 |  | Installed | True Refrigeration | PO-2026-0005 | 2025-01-03 | 2025-05-18 | 2025-06-04 |  |  | 2025-06-01 | GC
6 | VIP suite furnishings | Kitchen/F&B | 150 | GL | 22773.15 |  | Installed | Steelcase Inc. | PO-2026-0006 | 2025-05-23 | 2025-11-04 | 2025-11-22 |  |  | 2025-11-15 | Owner
7 | Kitchen prep line equipment | Kitchen/F&B | 1 | SET | 23163.74 |  | Received | American Seating | PO-2026-0007 | 2025-04-07 | 2025-07-16 | 2025-08-02 |  |  | 2025-08-19 | Vendor | Notes for item 7
8 | Wayfinding signage package | AV/Technology | 344 | PR | 173.51 |  | Received | Herman Miller | PO-2026-0008 | 2025-01-25 | 2025-04-21 | 2025-05-02 |  |  | 2025-04-28 | GC | Notes for item 8
9 | Locker room benches & lockers | AV/Technology | 258 | UNIT | 12611.67 |  | Ordered | GE Current | PO-2026-0009 | 2025-07-29 | 2026-01-14 |  |  |  | 2026-01-30 | Vendor
10 | Press box desks & chairs | Signage | 312 | EA | 15375.45 |  | Ordered | Sysco Equipment | PO-2026-0010 | 2025-06-17 | 2025-10-26 |  |  |  | 2025-11-14 | GC
11 | Jumbotron secondary display | Equipment | 484 | RL | 12917.7 |  | Complete | Herman Miller | PO-2026-0011 | 2025-03-11 | 2025-05-02 | 2025-05-21 |  |  | 2025-05-10 | GC | Notes for item 11
12 | Point-of-sale terminals | Signage | 93 | UNIT | 1094.28 |  | Shipped | American Seating | PO-2026-0012 | 2025-03-13 | 2025-06-05 |  |  |  | 2025-07-08 | Owner
13 | Stadium lighting system | Equipment | 356 | LF | 10061.52 |  | Shipped | Hobart Corp | PO-2026-0013 | 2025-08-21 | 2026-01-29 |  |  |  | 2026-02-22 | Vendor
14 | Restroom fixtures & partitions | Uniforms | 425 | BOX | 6474.16 |  | Not Started | Yamaha Commercial | PO-2026-0014 | 2025-01-29 | 2025-07-16 |  |  |  | 2025-08-28 | Vendor
15 | Hospitality lounge furniture | Kitchen/F&B | 379 | EA | 3724.06 |  | Ordered | Daktronics | PO-2026-0015 | 2025-10-18 | 2025-12-27 |  |  |  | 2026-02-07 | Vendor
16 | Broadcast camera positions | Equipment | 271 | EA | 13747.95 |  | Ordered | Yamaha Commercial | PO-2026-0016 | 2025-02-02 | 2025-03-17 |  |  |  | 2025-04-19 | GC | Notes for item 16
17 | Refrigeration units | Furniture | 68 | LF | 8753.49 |  | Received | Samsung Display | PO-2026-0017 | 2025-10-06 | 2026-03-06 | 2026-02-28 |  |  | 2026-04-18 | Owner | Notes for item 17
18 | Menu board digital signage | Kitchen/F&B | 105 | EA | 8313.01 |  | Complete | ASM Global | PO-2026-0018 | 2025-05-19 | 2025-06-07 | 2025-06-08 |  |  | 2025-07-18 | Owner | Notes for item 18
19 | Field lighting towers | Signage | 100 | RL | 18955.32 |  | Shipped | Bose Pro | PO-2026-0019 | 2025-09-01 | 2025-10-21 |  |  |  | 2025-11-23 | Vendor
20 | Athletic training equipment | Art/Decor | 100 | SET | 21534.03 |  | Not Started | American Seating | PO-2026-0020 | 2025-04-19 | 2025-07-29 |  |  |  | 2025-08-09 | Vendor
21 | PA system speakers | AV/Technology | 496 | PR | 21799.17 |  | Shipped | JBL Professional | PO-2026-0021 | 2025-07-17 | 2025-12-16 |  |  |  | 2026-01-07 | Owner
22 | Luxury suite bar stools | Textiles | 326 | LF | 21551.05 |  | Installed | GE Current | PO-2026-0022 | 2025-06-01 | 2025-08-14 | 2025-08-30 |  |  | 2025-08-25 | Vendor
23 | Exhaust hood system | Uniforms | 425 | EA | 3869.01 |  | Shipped | Steelcase Inc. | PO-2026-0023 | 2025-01-15 | 2025-02-07 |  |  |  | 2025-03-24 | Vendor
24 | Entrance canopy signage | Uniforms | 225 | SF | 9648.23 |  | Installed | Bose Pro | PO-2026-0024 | 2026-02-05 | 2026-04-22 | 2026-05-04 |  |  | 2026-06-03 | Vendor
25 | Locker room flooring | Uniforms | 179 | GL | 16969.67 |  | Complete | Herman Miller | PO-2026-0025 | 2026-01-23 | 2026-04-02 | 2026-03-29 |  |  | 2026-04-18 | GC | Notes for item 25
26 | Concourse seating | Signage | 279 | UNIT | 24878.8 |  | Not Started | Hobart Corp | PO-2026-0026 | 2025-06-19 | 2025-07-20 |  |  |  | 2025-08-17 | Vendor
27 | Back-of-house shelving | Signage | 205 | SF | 11228.33 |  | Not Started | Philips Lighting | PO-2026-0027 | 2025-11-19 | 2026-01-16 |  |  |  | 2026-02-15 | GC | Notes for item 27
28 | Security camera system | Equipment | 380 | EA | 11890.23 |  | Complete | Ferguson Enterprises | PO-2026-0028 | 2025-10-31 | 2025-12-09 | 2025-12-02 |  |  | 2026-01-10 | Vendor
29 | Ticket booth fixtures | Textiles | 197 | SET | 18716.82 |  | Received | GE Current | PO-2026-0029 | 2025-10-28 | 2026-02-02 | 2026-02-16 |  |  | 2026-03-19 | Vendor
30 | Team locker room lockers | Art/Decor | 437 | GL | 11953.94 |  | Not Started | Sysco Equipment | PO-2026-0030 | 2025-05-02 | 2025-05-18 |  |  |  | 2025-06-04 | Vendor
31 | Elevator cab finishes | Textiles | 494 | SF | 10416.37 |  | Complete | Yamaha Commercial | PO-2026-0031 | 2025-01-23 | 2025-05-07 | 2025-05-01 |  |  | 2025-05-31 | GC | Notes for item 31
32 | Stadium club chairs | Art/Decor | 46 | EA | 1894.74 |  | Installed | Samsung Display | PO-2026-0032 | 2025-05-14 | 2025-11-05 | 2025-11-04 |  |  | 2025-12-12 | Vendor
33 | Ice machine units | Furniture | 411 | RL | 24195.89 |  | Installed | JBL Professional | PO-2026-0033 | 2025-11-15 | 2026-04-04 | 2026-04-11 |  |  | 2026-04-28 | GC
34 | Directional signage interior | OS&E | 114 | RL | 17653.13 |  | Complete | Samsung Display | PO-2026-0034 | 2025-06-15 | 2025-07-09 | 2025-07-17 |  |  | 2025-07-16 | Vendor | Notes for item 34
35 | Field wall padding | OS&E | 310 | PR | 9258.75 |  | Shipped | Eaton Corp | PO-2026-0035 | 2026-05-07 | 2026-06-01 |  |  |  | 2026-07-05 | Vendor
36 | Warm-up area equipment | Art/Decor | 171 | GL | 378.08 |  | Received | ASM Global | PO-2026-0036 | 2025-08-18 | 2026-01-22 | 2026-02-02 |  |  | 2026-02-12 | Owner
37 | Broadcast booth desks | Kitchen/F&B | 240 | UNIT | 7931.55 |  | Installed | Steelcase Inc. | PO-2026-0037 | 2026-04-13 | 2026-07-12 | 2026-07-06 |  |  | 2026-08-26 | GC | Notes for item 37
38 | Concession trash receptacles | Equipment | 151 | UNIT | 9501.72 |  | Complete | Samsung Display | PO-2026-0038 | 2025-01-08 | 2025-01-24 | 2025-02-09 |  |  | 2025-01-31 | Owner
39 | HVAC control system | Kitchen/F&B | 135 | GL | 11077.81 |  | Complete | Philips Lighting | PO-2026-0039 | 2025-02-28 | 2025-03-26 | 2025-04-14 |  |  | 2025-04-23 | Owner | Notes for item 39
40 | Premium club bar top | OS&E | 213 | SF | 15147.37 |  | Complete | Eaton Corp | PO-2026-0040 | 2025-04-13 | 2025-07-11 | 2025-07-07 |  |  | 2025-07-26 | GC
41 | Fire suppression system | Textiles | 72 | SET | 21134.68 |  | Complete | Hobart Corp | PO-2026-0041 | 2025-03-17 | 2025-04-18 | 2025-04-10 |  |  | 2025-05-18 | Owner
42 | Exterior monument sign | Uniforms | 64 | BOX | 22743.85 |  | Shipped | Philips Lighting | PO-2026-0042 | 2026-04-04 | 2026-05-04 |  |  |  | 2026-05-15 | Owner
43 | Team bench seating | Art/Decor | 306 | LF | 6530 |  | Shipped | Herman Miller | PO-2026-0043 | 2025-10-07 | 2026-03-01 |  |  |  | 2026-03-20 | Vendor
44 | Medical/athletic training supplies | Textiles | 361 | SF | 8733.51 |  | Shipped | GE Current | PO-2026-0044 | 2025-02-18 | 2025-08-09 |  |  |  | 2025-09-09 | Owner
45 | Scoreboard controller | Equipment | 464 | EA | 15198 |  | Received | GE Current | PO-2026-0045 | 2025-09-12 | 2025-12-30 | 2026-01-17 |  |  | 2026-01-26 | GC
46 | Suite kitchenette cabinets | Signage | 304 | GL | 5344.04 |  | Not Started | JBL Professional | PO-2026-0046 | 2025-08-09 | 2026-01-11 |  |  |  | 2026-02-14 | Vendor
47 | Retail merchandise fixtures | Art/Decor | 332 | BOX | 3329.57 |  | Complete | Daktronics | PO-2026-0047 | 2025-05-20 | 2025-08-21 | 2025-08-31 |  |  | 2025-09-01 | GC
48 | Parking lot lighting | AV/Technology | 284 | EA | 19447.37 |  | Shipped | Eaton Corp | PO-2026-0048 | 2026-02-14 | 2026-06-21 |  |  |  | 2026-07-13 | GC
49 | Entry turnstile system | Textiles | 295 | UNIT | 15815.85 |  | Not Started | Booth & Partners | PO-2026-0049 | 2025-01-06 | 2025-04-01 |  |  |  | 2025-05-09 | Owner
50 | Hospitality carpet & rugs | OS&E | 246 | EA | 8547.86 |  | Installed | True Refrigeration | PO-2026-0050 | 2026-01-04 | 2026-03-09 | 2026-03-26 |  |  | 2026-04-21 | Owner
51 | Team meeting room tables | Kitchen/F&B | 330 | YD | 20250.03 |  | Ordered | Daktronics | PO-2026-0051 | 2025-06-25 | 2025-10-01 |  |  |  | 2025-11-15 | GC
52 | Dishwasher - commercial | Uniforms | 487 | UNIT | 1200.9 |  | Received | Booth & Partners | PO-2026-0052 | 2025-09-16 | 2025-10-28 | 2025-11-16 |  |  | 2025-12-05 | GC
53 | LED ribbon board | Textiles | 138 | LF | 11227.25 |  | Installed | Samsung Display | PO-2026-0053 | 2026-01-05 | 2026-03-25 | 2026-04-12 |  |  | 2026-04-16 | GC
54 | Office cubicle systems | Equipment | 75 | GL | 10989.7 |  | Shipped | Samsung Display | PO-2026-0054 | 2025-10-20 | 2025-12-12 |  |  |  | 2026-01-23 | GC
55 | Stadium chairback seats | Furniture | 230 | BOX | 920.74 |  | Not Started | Honeywell Building | PO-2026-0055 | 2025-11-20 | 2026-01-27 |  |  |  | 2026-02-14 | Vendor | Notes for item 55
56 | Kitchen storage racks | Signage | 190 | RL | 7431.62 |  | Received | Sysco Equipment | PO-2026-0056 | 2025-05-16 | 2025-07-30 | 2025-08-04 |  |  | 2025-08-12 | Vendor
57 | WiFi access points | Furniture | 308 | BOX | 11056.27 |  | Installed | Philips Lighting | PO-2026-0057 | 2026-03-29 | 2026-07-12 | 2026-07-28 |  |  | 2026-08-11 | Vendor
58 | Locker room mirrors | Art/Decor | 109 | GL | 15502.29 |  | Received | Booth & Partners | PO-2026-0058 | 2026-03-02 | 2026-06-05 | 2026-06-02 |  |  | 2026-07-01 | Vendor | Notes for item 58
59 | Field goal posts | Uniforms | 138 | LF | 23825.59 |  | Complete | ASM Global | PO-2026-0059 | 2025-04-12 | 2025-06-17 | 2025-06-16 |  |  | 2025-07-25 | Vendor | Notes for item 59
60 | Concession warmers | Art/Decor | 466 | BOX | 5235.05 |  | Complete | Daktronics | PO-2026-0060 | 2025-05-15 | 2025-06-29 | 2025-06-28 |  |  | 2025-08-06 | Vendor
61 | Lobby reception desk | Furniture | 225 | SF | 1947.14 |  | Ordered | JBL Professional | PO-2026-0061 | 2026-01-01 | 2026-04-06 |  |  |  | 2026-04-23 | Vendor | Notes for item 61
62 | Drapes & window treatments | Signage | 487 | PR | 14202.24 |  | Not Started | ASM Global | PO-2026-0062 | 2025-10-19 | 2025-11-17 |  |  |  | 2025-12-19 | GC
63 | Athletic field paint | Textiles | 82 | YD | 20873.39 |  | Received | Booth & Partners | PO-2026-0063 | 2026-01-30 | 2026-05-19 | 2026-05-25 |  |  | 2026-06-13 | Owner
64 | Player recovery equipment | Art/Decor | 147 | GL | 17907.15 |  | Complete | Steelcase Inc. | PO-2026-0064 | 2025-06-01 | 2025-11-10 | 2025-11-04 |  |  | 2025-12-24 | Vendor
65 | Video wall displays | Equipment | 200 | GL | 17808.42 |  | Not Started | Honeywell Building | PO-2026-0065 | 2025-08-12 | 2026-01-02 |  |  |  | 2026-02-05 | Vendor
66 | Bar glassware & smallware | Furniture | 452 | GL | 13211.4 |  | Installed | GE Current | PO-2026-0066 | 2025-10-09 | 2025-11-18 | 2025-11-26 |  |  | 2025-12-18 | Owner | Notes for item 66
67 | Acoustic wall panels | Signage | 100 | UNIT | 23905.34 |  | Not Started | Philips Lighting | PO-2026-0067 | 2025-11-22 | 2026-04-27 |  |  |  | 2026-06-07 | GC | Notes for item 67
68 | Uniform storage cabinets | OS&E | 253 | SF | 16118.94 |  | Not Started | Bose Pro | PO-2026-0068 | 2025-05-21 | 2025-06-15 |  |  |  | 2025-06-23 | GC
69 | Concession beverage dispensers | Art/Decor | 236 | BOX | 21133.48 |  | Not Started | GE Current | PO-2026-0069 | 2025-11-13 | 2026-05-03 |  |  |  | 2026-06-17 | GC | Notes for item 69
70 | Entry gate hardware | Art/Decor | 51 | BOX | 7451.58 |  | Ordered | GE Current | PO-2026-0070 | 2025-09-24 | 2026-02-14 |  |  |  | 2026-03-27 | Owner
71 | Team treadmill equipment | Art/Decor | 282 | UNIT | 11863.85 |  | Installed | JBL Professional | PO-2026-0071 | 2026-02-09 | 2026-07-10 | 2026-07-18 |  |  | 2026-07-18 | Owner
72 | Laundry equipment | Kitchen/F&B | 221 | YD | 18616.03 |  | Installed | Hobart Corp | PO-2026-0072 | 2025-08-21 | 2025-10-20 | 2025-10-15 |  |  | 2025-11-20 | GC
73 | Suite refrigerator units | Art/Decor | 393 | PR | 7474.14 |  | Ordered | Steelcase Inc. | PO-2026-0073 | 2025-04-16 | 2025-07-02 |  |  |  | 2025-08-05 | GC
74 | Wall art & photo murals | Furniture | 70 | YD | 6602.97 |  | Complete | Honeywell Building | PO-2026-0074 | 2025-12-01 | 2026-02-23 | 2026-03-03 |  |  | 2026-04-08 | Owner
75 | First aid stations | AV/Technology | 43 | YD | 6488.35 |  | Not Started | Samsung Display | PO-2026-0075 | 2025-02-07 | 2025-06-15 |  |  |  | 2025-06-22 | Owner
76 | Ticket printer equipment | Uniforms | 289 | SF | 2183.88 |  | Complete | Hobart Corp | PO-2026-0076 | 2026-02-02 | 2026-07-18 | 2026-07-12 |  |  | 2026-08-15 | Vendor
77 | Field maintenance tools | Signage | 291 | GL | 4826.01 |  | Installed | Ferguson Enterprises | PO-2026-0077 | 2025-06-25 | 2025-12-06 | 2025-12-19 |  |  | 2026-01-15 | GC
78 | Stadium bowl handrails | OS&E | 465 | SET | 19703.65 |  | Received | True Refrigeration | PO-2026-0078 | 2025-04-08 | 2025-09-08 | 2025-09-28 |  |  | 2025-10-12 | Vendor
79 | Concession sneeze guards | Equipment | 29 | SF | 1122.93 |  | Complete | True Refrigeration | PO-2026-0079 | 2025-08-08 | 2025-11-02 | 2025-10-24 |  |  | 2025-12-02 | GC | Notes for item 79
80 | PA amplifier racks | Furniture | 48 | YD | 2245.14 |  | Installed | Eaton Corp | PO-2026-0080 | 2025-08-18 | 2025-12-12 | 2026-01-01 |  |  | 2026-01-12 | GC
81 | Team meeting room chairs | Uniforms | 129 | SET | 6549.37 |  | Complete | Ferguson Enterprises | PO-2026-0081 | 2025-03-03 | 2025-08-30 | 2025-08-27 |  |  | 2025-10-10 | GC | Notes for item 81
82 | Kitchen utensil kits | Kitchen/F&B | 69 | RL | 8774.41 |  | Complete | American Seating | PO-2026-0082 | 2026-04-23 | 2026-10-09 | 2026-10-06 |  |  | 2026-10-19 | Vendor
83 | Signage - sponsor panels | Furniture | 206 | UNIT | 11246.54 |  | Not Started | ASM Global | PO-2026-0083 | 2025-06-24 | 2025-12-14 |  |  |  | 2026-01-14 | Vendor
84 | Gym floor covers | Signage | 121 | SET | 13595.14 |  | Not Started | Sherwin-Williams | PO-2026-0084 | 2025-01-06 | 2025-05-01 |  |  |  | 2025-06-10 | GC | Notes for item 84
85 | Training sleds & pads | Art/Decor | 436 | GL | 18950.94 |  | Shipped | Philips Lighting | PO-2026-0085 | 2025-02-13 | 2025-05-20 |  |  |  | 2025-06-20 | Owner
86 | Matrix board displays | OS&E | 167 | RL | 5372.04 |  | Not Started | ASM Global | PO-2026-0086 | 2025-10-07 | 2026-03-07 |  |  |  | 2026-04-10 | Owner
87 | Bar refrigeration | Signage | 311 | SET | 10232.64 |  | Complete | Hobart Corp | PO-2026-0087 | 2026-04-12 | 2026-05-18 | 2026-06-05 |  |  | 2026-06-22 | Vendor
88 | Lobby seating group | AV/Technology | 500 | SF | 13100.03 |  | Complete | ASM Global | PO-2026-0088 | 2026-05-03 | 2026-05-30 | 2026-06-03 |  |  | 2026-07-14 | Owner | Notes for item 88
89 | Window blinds - all zones | Art/Decor | 239 | PR | 20937.72 |  | Not Started | Steelcase Inc. | PO-2026-0089 | 2025-07-09 | 2025-09-01 |  |  |  | 2025-10-13 | Vendor | Notes for item 89
90 | Team logo mats | Textiles | 382 | EA | 20549.75 |  | Shipped | Philips Lighting | PO-2026-0090 | 2026-05-01 | 2026-10-27 |  |  |  | 2026-11-08 | Vendor
91 | Concession POS tablets | Kitchen/F&B | 242 | SET | 1798.35 |  | Not Started | Samsung Display | PO-2026-0091 | 2025-10-18 | 2025-11-30 |  |  |  | 2026-01-14 | GC
92 | Field chalk & lining tools | Furniture | 207 | SF | 22148.7 |  | Not Started | American Seating | PO-2026-0092 | 2026-01-08 | 2026-06-06 |  |  |  | 2026-07-01 | Owner
93 | HDMI switching system | AV/Technology | 433 | LF | 13656.76 |  | Shipped | Philips Lighting | PO-2026-0093 | 2025-09-08 | 2025-11-03 |  |  |  | 2025-11-26 | Owner
94 | Suite cabinet hardware | OS&E | 22 | PR | 7262.57 |  | Shipped | Sherwin-Williams | PO-2026-0094 | 2025-07-12 | 2025-08-23 |  |  |  | 2025-09-09 | Vendor
95 | Athletic tape & supplies | Furniture | 285 | PR | 2304.85 |  | Complete | JBL Professional | PO-2026-0095 | 2026-02-08 | 2026-03-09 | 2026-03-09 |  |  | 2026-04-10 | GC
96 | Stadium evacuation signage | AV/Technology | 325 | YD | 17964.62 |  | Ordered | Hobart Corp | PO-2026-0096 | 2026-02-24 | 2026-07-18 |  |  |  | 2026-07-29 | Owner
97 | Server rack equipment | Kitchen/F&B | 101 | EA | 21882.99 |  | Ordered | Steelcase Inc. | PO-2026-0097 | 2025-02-11 | 2025-04-12 |  |  |  | 2025-04-26 | Vendor
98 | Kitchen mobile carts | Textiles | 50 | SET | 52.96 |  | Complete | Daktronics | PO-2026-0098 | 2025-04-01 | 2025-05-06 | 2025-05-25 |  |  | 2025-06-15 | Vendor | Notes for item 98
99 | Fan experience photo booth | Equipment | 500 | LF | 14767.01 |  | Installed | Steelcase Inc. | PO-2026-0099 | 2025-11-12 | 2025-12-08 | 2025-11-29 |  |  | 2026-01-03 | Owner
100 | Team branded flags | Uniforms | 153 | EA | 22816.52 |  | Installed | Daktronics | PO-2026-0100 | 2025-08-30 | 2025-11-13 | 2025-11-20 |  |  | 2025-12-11 | Owner
SUMMARY BY STATUS
Status | Count
Not Started
Ordered
Shipped
Received
Installed
Complete
SUMMARY BY CATEGORY
Category | Count
Furniture
Equipment
AV/Technology
Kitchen/F&B
Signage
Textiles
Art/Decor
OS&E
Uniforms
TOTAL ITEMS